Week 8 - Launch Crisis Playbook

PixelPay Day-End Summary | GTM Plan, 100% Launch, and 6 Hour Incident Response

| PM | Amandeep Kaur | PMM Partner | Sneha Iyer |
| --- | --- | --- | --- |
| Launch Tier | Tier 2 - Feature Launch | Launch Decision | 100% rollout after winning A/B test |
| A/B Result | D7 retention +6 percentage points | Crisis Rule | Rollback -> Diagnose -> Communicate |
| Executive decision Proceed with a 100% launch because the Week 7 A/B test won with D7 retention up 6 points and guardrails are assumed healthy. The launch remains operationally reversible through a feature flag. If the wrong-total crisis crosses the threshold, the PM rolls back first before any diagnosis debate. |  |  |  |

# 1. Context and Launch Objective

The Day-End Summary has moved from experiment to launch candidate. The Week 7 A/B test showed a 6 percentage point lift in D7 retention, which is above the planned 5 percentage point minimum detectable effect. The launch objective is to turn the feature into a trusted daily ritual for merchants without creating confusion about money movement, settlement status, or total amount calculations.

Launch objective: ship Day-End Summary to 100% of eligible active merchants, drive repeat evening app opens, and keep trust guardrails flat.

Primary launch outcome: sustain the D7 retention lift while expanding from test cohort to all eligible merchants.

Merchant promise: today's collections, pending settlement, and net-to-bank are visible in one glance.

Operational promise: support, PMM, data, and engineering can detect issues and reverse the launch quickly.

# 2. Positioning Statement with Sneha

Positioning uses the Geoffrey Moore template so the message is specific, differentiated, and merchant-centered.

| Template element | Statement |
| --- | --- |
| FOR | Indian SMB merchants closing shop after a long day |
| WHO | struggle to know where the day's money ended up without opening multiple apps or checking manual notes |
| OUR | PixelPay Day-End Summary |
| IS A | one-glance evening summary screen with a scheduled close-of-day reminder |
| THAT | shows today's earnings, pending settlements, refunds, and net-to-bank clearly in Hindi or English |
| UNLIKE | opening 3 apps or manually reconciling collections at closing time |
| WE | make the daily money check feel fast, trustworthy, and as natural as opening WhatsApp at shop close. |

# 3. Five-Phase Launch Checklist

| Phase | Window | Owner | Checklist | Exit criteria |
| --- | --- | --- | --- | --- |
| P1 - Pre-launch readiness | T-14 to T-7 days | PM + Eng + PMM + Support | Final spec frozen; QA on totals, refunds, settlement windows, language copy; support macros approved; dashboards live; rollback flag tested. | No P0/P1 bugs; all launch owners sign off. |
| P2 - Launch rehearsal | T-7 to T-1 day | PM + Data + Support | Dry run 5 merchant examples end-to-end; compare ledger vs summary; test 8 PM push; verify FAQ and help center; run incident simulation. | Data parity checks pass; support can answer top 10 questions. |
| P3 - 100% launch | T day, 9:00 AM | PM as launch DRI; Eng on call | Enable Day-End Summary for 100% eligible merchants; publish in-app banner; send email/WhatsApp copy; keep feature flag reversible. | Feature live; dashboards green for first 60 minutes. |
| P4 - Hypercare monitoring | T+0 to T+7 days | PM + Riya + Support | Hourly checks on tickets, wrong-total keywords, crash rate, push opt-outs, data freshness, and settlement mismatch reports. | No rollback trigger crossed; daily launch summary posted. |
| P5 - Retrospective and v2 | T+14 to T+21 days | Full squad | Review adoption, retention, support themes, incident readiness, and missed QA cases; prioritize v2 improvements. | Decision made: scale messaging, iterate, or relaunch after fix. |

# 4. In-App Messaging Design

The launch message should explain value quickly, avoid over-claiming, and reduce support confusion around totals and settlement timing.

| Surface | Headline | Body copy | CTA | Rule |
| --- | --- | --- | --- | --- |
| Entry banner | Your day, summed up. | See today's collections, pending settlements, refunds, and net-to-bank in one view. | View summary | Shown once on app open after launch; dismissible. |
| 8 PM push | Day-End Summary is ready | Check today's total and what will reach your bank. | Open PixelPay | Localized to merchant close-time where available. |
| First-use tooltip | Pending settlement is not missing money. | It means the amount is collected but not yet paid out to your bank. | Got it | Reduces panic tickets around settlement timing. |
| Error state | Summary temporarily unavailable | Your payments and payouts are safe. Please check again shortly. | Retry | Clear money-safety reassurance; no blame on user. |
| Hindi/Hinglish variant | Aaj ka hisaab taiyaar hai | Aaj ki collection, pending settlement aur bank mein aane wali rakam ek jagah dekhein. | Summary dekhein | For Hindi-preferred merchants. |

# 5. Support and PMM Readiness

Support training: train agents on definitions of total collected, refund adjustment, pending settlement, and net-to-bank.

Ticket taxonomy: tag incoming issues as summary_total_wrong, settlement_confusion, push_irritation, language_confusion, or crash.

Escalation: any money amount discrepancy from 10+ merchants in 30 minutes goes to the incident channel immediately.

PMM assets: in-app copy, email, WhatsApp copy, help center article, short video script, and Hindi/English FAQ.

Data dashboards: retention, daily opens, push CTR, support tickets per 1,000 merchants, wrong-total keyword count, and crash rate.

# 6. 100% Launch Execution Record

| Time | Action | Owner | Status / note |
| --- | --- | --- | --- |
| 8:30 AM | Final go/no-go: QA, data freshness, support staffing, rollback flag, PMM assets. | PM + Eng + Data + Support | Go if all readiness gates are green. |
| 9:00 AM | Enable feature flag day_end_summary_v2 for 100% eligible merchants. | Engineering | Launch begins; old view remains available as fallback. |
| 9:05 AM | In-app banner and help-center article live. | PMM | Sneha confirms copy is published. |
| 9:15 AM | Support war room opens for first-day monitoring. | Support Lead | Macros and escalation paths ready. |
| 10:00 AM onward | Hourly monitoring of guardrails and wrong-total keyword spikes. | PM + Riya | Post update in #launch-day-end-summary. |

# 7. Rollback Trigger - Defined Before the Crisis

Non-negotiable trigger If 200 or more merchants report "total amount is wrong" within 6 hours, OR support tickets exceed 75 per 1,000 merchants per week, OR any credible money-amount discrepancy appears, the PM rolls back immediately. Who decides: PM Incident Commander, with Engineering Lead confirming execution. Diagnosis does not delay rollback.

Why this threshold matters: this is a trust-sensitive money surface. Even if the underlying ledger is safe, merchants seeing wrong numbers damages confidence. The feature is reversible, so the correct PM move is to stop exposure first and investigate after users are protected.

# 8. Six-Hour Crisis Response: Rollback -> Diagnose -> Communicate

Incident: six hours after 100% launch, support receives 200 merchant tickets saying "total amount is wrong." This crosses the rollback threshold. The playbook below must be executed in order.

| Timebox | Phase | Actions | Owner | Exit condition |
| --- | --- | --- | --- | --- |
| 0-15 min | 1. ROLLBACK FIRST | Declare P0/P1 launch incident; disable day_end_summary_v2 for 100%; revert to old summary view; pause 8 PM push; stop PMM reminders; confirm old view is live. | PM Incident Commander + Eng Lead | No additional merchants see the suspected wrong total. |
| 15-60 min | 2. DIAGNOSE SECOND | Pull affected merchant IDs; compare raw ledger vs summary calculation; check timezone cut-off, refunds, chargebacks, settlement delays, cache freshness, and release diff; reproduce with 5 affected accounts. | Riya + Eng + QA | Root-cause hypothesis and affected segment identified. |
| 60-120 min | 3. COMMUNICATE THIRD | Send merchant, support/team, and leadership updates. Be early, honest, and clear that the feature was reverted while the team validates totals. | PM + Sneha + Support Lead | All audiences hear from PixelPay before rumors spread. |
| 24 hours | Fix and validation | Patch calculation or data freshness bug; replay affected examples; add regression tests; QA in Hindi/English; update support article. | Eng + QA + Data | Fix verified against affected merchants and synthetic cases. |
| 48-72 hours | Controlled relaunch | Relaunch to 5%, then 25%, then 100% only if wrong-total tickets remain below threshold and data parity is clean. | PM + Eng + Riya | Feature returns safely with better monitoring. |

# 9. Diagnosis Plan

Segment check: identify whether the issue is concentrated by city, language, bank, merchant category, settlement cycle, app version, or transaction volume.

Calculation check: compare total collected, refunds, failed payments, chargebacks, and settlement deductions against the raw ledger.

Timing check: test day-boundary logic, timezone handling, cut-off times, and late-arriving settlement events.

Data pipeline check: verify cache invalidation, ETL job completion, duplicate transactions, and delayed reconciliation updates.

Release diff check: review the exact code/config changes shipped between A/B test and 100% launch.

Reproduction: use at least 5 affected merchant IDs and 5 clean merchant IDs to prove the root cause and verify the fix.

# 10. Communication Templates

Communication happens after rollback is underway, not before. The goal is to protect trust without pretending we already know the full answer.

| Audience | Message |
| --- | --- |
| Merchant message | We have temporarily switched back to the previous summary view while we fix an issue in the new Day-End Summary. Your payments and bank payouts are not being changed by this display issue. We are checking affected accounts and will update you shortly. Thank you for your patience. |
| Support/team message | Incident declared for Day-End Summary wrong-total reports. Rollback is complete/in progress. Please tag tickets as summary_total_wrong, reassure merchants that payments are safe, do not speculate on root cause, and escalate merchant IDs with screenshots to #incident-day-end-summary. |
| Leadership message | Six hours after 100% launch, we crossed the rollback threshold with 200 wrong-total tickets. We rolled back the feature first, paused pushes, and are diagnosing ledger-vs-summary differences. Current focus: isolate affected segment, verify payout safety, and provide the next update in 60 minutes. |

# 11. Postmortem Plan

The crisis is not closed when the feature is fixed. It closes when the team has learned why the launch checklist missed the issue and updated the system so it is harder to repeat.

| Postmortem area | Review question / output |
| --- | --- |
| What failed? | Was the error in calculation logic, data freshness, settlement timing, caching, localization, or launch-only scale conditions? |
| Why did QA miss it? | Which scenario was absent from the pre-launch checklist: refunds, multi-bank settlements, timezone cut-off, late events, or high-volume merchants? |
| Why did the A/B pass? | Was the 10% cohort unrepresentative, or did the bug appear only after 100% scale, copy changes, or data pipeline load? |
| Detection quality | Did dashboards alert before support tickets? Were wrong-total keyword alerts and anomaly thresholds set correctly? |
| Process changes | Add ledger parity test, launch-scale load test, synthetic merchant accounts, support keyword alert, and rollback drill before future money-surface launches. |

# 12. Final Submission Checklist

Positioning statement drafted with Sneha and tied to the merchant closing-time ritual.

Five-phase launch checklist includes readiness, rehearsal, 100% launch, hypercare, and retrospective.

In-app messaging covers banner, push, tooltip, error state, and Hindi/Hinglish variant.

Launch execution explicitly moves to 100% eligible merchants with a reversible feature flag.

Crisis playbook follows the required order: rollback first, diagnose second, communicate third.

Rollback trigger and decision owner are defined before the crisis.

Merchant, team, and leadership messages are included.

Postmortem explains how the launch checklist will improve after the incident.

# Sources Used

Week-08-Launch-Plan-Sample.md - used as the structure reference for launch tier, positioning, launch phases, rollback threshold, and crisis flow.

Project-8_Clue-Sheet.pdf - used as the method reference for the strict rollback, diagnosis, communication, and postmortem sequence.